December 19, 2019

# FOOD LION STORE #1458 LAUREL, MD - REMODEL SCHEDULE DRAFT

Monday, Jan. 20th (Day)	                  						                              MOBILZE

- General Contractor to begin mobilizing to the site.

- Loss Prevention needs to have a camera on existing truck door used for construction entrance.

- Note:  General Contractor must coordinate with the Store Manager on Wednesday prior to the coming week on which nights someone has to stay overnight and go over the schedule for the next two weeks.

Wednesday, Jan. 22nd (Day)

- Pre-construction/schedule Coordination Meeting between the Store Personnel, General Contractor (Project Manager and Superintendent), Refrigeration Contractor, Energy Team and the Retail Specialist.  All MUST BE PRESENT at 10:00 am.

- Store Manager must have an area set up for approximately 20 people in the backroom.

- General Contractor to verify that all subs have ordered ALL equipment for the remodel.  Delays 
will not be tolerated. Provide the Construction Supervisor proof of order for all of the General 
Contractors and Sub’s equipment within the next two weeks.

- General Contractor must have a 24 Hour contact list present to give to the Store Manager. 
Please keep this list in the Notebook.

- General Contractor must install new remodel Food Lion banners and store front banners.  Note:  Exterior remodel banner must have a 1”x4” wood frame and remain up throughout the remodel.

- General Contractor and Construction Manager to walk the store for future décor issues that will need to be handled prior to the two week décor install.  Contact Aaron Ashely @704-310-3128 for fire alarm equipment that will need to be relocated and a designated time frame.

- General Contractor to introduce the clean-up person hired by the General Contractor to the Store 
Manager

- Construction Manager and General Contractor must meet to discuss the floor tile layout.

- Construction Manager, Energy Manager, Maintenance Supervisor, Refrigeration Contractor and General Contractor to review plans for hub drain and pit locations.

- General Contractor to contact Construction Manager to schedule the Coinstar to be temporarily removed in 2 weeks.

- General Contractor to contact Construction Manager to schedule the ATM to be temporarily removed in 2 weeks.

- NOTE:  All the incoming construction material placed in the RED ZONE and the Bill of Lading placed in the office notebook.

Monday, Jan. 27th (Day)	                           MINI RESET/ BACKROOM AREA, OFFICE, DMO, PCT WORK

- Mini Reset to remove 28’ of shelving on left wall beside existing dairy cases.

- General Contractor to start Backroom and Office work:  Dept. Manager’s Office/PC Training Room, Lounge, and Work Room.  To be complete by April 10th.

- General Contractor to in fill meat prep windows by February 21st

- General Contractor to confirm all national accounts orders with the Construction Manager.

- Electrical Contractor to have ALL appropriate breakers and lights ordered to complete the remodel.

- Plumbing Contractor to have ALL appropriate deli equipment ordered to complete on schedule.

- Plumbing Contractor to verify drain locations for cases to avoid any delays during the case moves.

Tuesday, Jan. 28th (Day)

- Deliver:

- Security Cage

- Condensers

- (1) Ice Cream Freezer evaporator.

- (2) Dairy Cooler

- (1) Meat Cooler

- (1) Produce Cooler

- (1) Deli Cooler

Monday, February 3rd (Night)                                                                                       DAIRY CHANGE OUTS

- Store Associates to remove product from Dairy cases #39 thru #43; wash down by 9:00 PM.

- Refrigeration Contractor to remove:

    - 60’ L6DL Dairy cases #39 thru #43 (A20, A21. A22)

- Deliver and Install:

- 60’ DX6LN Dairy case N33, N34, N35, N36, N37 (A20)

- All cases will be picked up by purchasing vendor.

- Plumbing Contractor must be on site to relocate the hub drains as required.

- General Contractor must patch and repair holes in the floor prior to the store opening.

- General Contractor must have the area cleaned up and safe for the public prior to leaving the site

- General Contractor to start trenching for new Frozen Food endcap (N59)

Tuesday, February 4th (Day)

- Dairy Reset to begin

Tuesday, February 4th (Night)

- Store Associates to remove product from Dairy cases #44 and #45; wash down by 9:00 PM.

- Refrigeration Contractor to remove:

    - 24’ L6DL Dairy cases #44 and #45 (A19)

- Deliver and Install:

- 52’ DX6LN Dairy case N38, N39, N40, N41, N42 (A19)

- All cases will be picked up by purchasing vendor.

- Plumbing Contractor must be on site to relocate the hub drains as required.

- General Contractor must patch and repair holes in the floor prior to the store opening.

- General Contractor must have the area cleaned up and safe for the public prior to leaving the site

Wednesday, February 5th (Day)

- Dairy Reset cont’d

Sunday, February 9th (Day)                                                                                ICE CREAM CHANGE OUTS

- This is a lot of work so will need to start earlier than normal each night this week.  "BIG NIGHT"

- Store Associates to remove product from Ice Cream cases #46 thru #51; wash down by 8:00 PM.

- Refrigeration Contractor to remove:

    - 3 Door L5FG Ice Cream endcap #46 (B14)

    - 24 Door L5FG cases #47 thru #51 (B13, B14)

- Deliver and Install:

- 3 Door QIV5V14 Frozen Food endcap N43 (B14)

- 23 Door QIV5V14 Ice Cream cases N44, N45, N46, N47, N48 (B13, B14)

- All cases will be picked up by purchasing vendor.

- Plumbing Contractor must be on site to relocate the hub drains as required.

- General Contractor must patch and repair holes in the floor prior to the store opening.

- General Contractor must have the area cleaned up and safe for the public prior to leaving the site

Monday, February 10th (Day)

- Ice Cream Reset to begin

Monday, February 10th (Night)

- This is a lot of work so will need to start earlier than normal each night this week.  "BIG NIGHT"

- Store Associates to remove product from Frozen Food cases #52 thru #57; wash down by 8:00 PM.

- Refrigeration Contractor to remove:

    - 3 Door L5FG Frozen Food endcap #54 (B12)

    - 21 Door L5FG Frozen Food cases #52, #53 and #55 thru #57 (B10, B11, B12)

- Deliver and Install:

- 8 Door QIV5V14 Frozen Food cases N49, N50 (B12)

- 15 Door QIV5V14 Frozen Food cases N52, N53 and N54 (B10)

- All cases will be picked up by purchasing vendor.

- Plumbing Contractor must be on site to relocate the hub drains as required.

- General Contractor must patch and repair holes in the floor prior to the store opening.

- General Contractor must have the area cleaned up and safe for the public prior to leaving the site

Tuesday, February 11th (Day)

- Frozen Food Reset to begin

Tuesday, February 11th (Night)

- Store Associates to remove product from Frozen Food cases #58 thru #60; wash down by 9:00 PM.

- Refrigeration Contractor to remove:

    - 15 Door L5FG Frozen Food #58, #59 and #60 (B9)

- Deliver and Install:

- 16 Doors QIV5V14 Frozen Food cases N55, N56, N57, N58 (B9)

- 4’ DX6LN Dairy Promo case N51 (A21)

- All cases will be picked up by purchasing vendor.

- Plumbing Contractor must be on site to relocate the hub drains as required.

- General Contractor must patch and repair holes in the floor prior to the store opening.

- General Contractor must have the area cleaned up and safe for the public prior to leaving the site

Wednesday, February 12th (Day)

- Frozen Food Reset to continue

Wednesday, February 12th (Night)

- This is a lot of work so will need to start earlier than normal each night this week.  "BIG NIGHT"

- Store Associates to remove product from Frozen Food cases #61 thru #64; wash down by 8:00 PM.

- Refrigeration Contractor to remove:

    - 20 Door L5FG Frozen Food #61 thru #64 (B6, B7)

- Deliver and Install:

- 17 Doors QIV5V14 Frozen Food cases N60, N61, N62, N63 (B7)

- All cases will be picked up by purchasing vendor.

- Plumbing Contractor must be on site to relocate the hub drains as required.

- General Contractor must patch and repair holes in the floor prior to the store opening.

- General Contractor must have the area cleaned up and safe for the public prior to leaving the site

Thursday, February 13th (Day)

- Frozen Food Reset to continue

Monday, February 17th (Night)                                                                        FROZEN FOOD CHANGE OUT

- General Contractor/Plumbing Contractor start trenching for new end cap. Complete this week.

- NOTE:  Install ¼” Steel Plate over any open trenches or pits and tape down carpet over plates.  Leave No trip hazards!!!!!!!!!!!!!!!!

- Store Associates to remove product from Frozen Food cases #65 thru #67; wash down by 9:00 PM.

- Refrigeration Contractor to remove:

    - 10 Door L5FG Frozen Food #65 and #66 (B8)

    - 3 Door L5FG Frozen Food endcap #67 (B8)

- Deliver and Install:

- 15 Doors QIV5V14 Frozen Food cases N64, N65, N66 (B8)

- 3 Doors QIV5V14 Ice Cream endcap N67 (B6)

- 3 Doors QIV5V14 Frozen Food endcap N59 (B6)

- All cases will be picked up by purchasing vendor.

- Plumbing Contractor must be on site to relocate the hub drains as required.

- General Contractor must patch and repair holes in the floor prior to the store opening.

- General Contractor must have the area cleaned up and safe for the public prior to leaving the site

Tuesday, February 18th (Day)

- Frozen Food Reset to continue

Tuesday, February 18th (Night)

- Store Associates to remove product from cases #34 thru #38; wash down by 9:00 PM.

- Refrigeration Contractor to remove:

    - 5 Door L5FG Meat/Seafood case #34 (B5)

    - 9 Door L5FG Frozen Food cases #35 and #36 (B5)

    - 16’ L6DLR Dairy cases N37, N38 (A23)

- Deliver and Install:

- 10 Doors QIV5V14 Frozen Food cases N31, N32 (B5)

- 10 Doors QIV5V14 Frozen Meat/ Seafood cases N29, N30 (B5)

- All cases will be picked up by purchasing vendor.

- Plumbing Contractor must be on site to relocate the hub drains as required.

- General Contractor must patch and repair holes in the floor prior to the store opening.

- General Contractor must have the area cleaned up and safe for the public prior to leaving the site

Wednesday, February 19th (Day)

- Frozen Food Reset to continue

Thursday, February 20th (Day)

- Deliver:

- Lunch Meat Grid System (Hold for Reset)

Monday, February 24th (Night)                                                  LUNCH MEAT RESET/ MEAT CHANGE OUT

- Store Associates to remove product from cases #11, #12, #22, #23 and #31 thru #33; wash down by 9:00 PM.

- Refrigeration Contractor to remove:

    - 36’ L4M Four-Deck Meat cases #31 thru #33 (A1, A2)

    - (2) 8’ LFW Meat Promo cases #22 and #23 (A3, B4)

    - 24’ L6DL Lunch Meat cases #11 and #12 (A13)

- Deliver and Install:

- 32’ LSB Lunch Meat cases N26, N27, N28 (A2)

- All cases will be picked up by purchasing vendor.

- Plumbing Contractor must be on site to relocate the hub drains as required.

- General Contractor must patch and repair holes in the floor prior to the store opening.

- General Contractor must have the area cleaned up and safe for the public prior to leaving the site

Tuesday, February 25th (Day)

- Lunch Meat Reset to begin.

Tuesday, February 25th (Night)

- Store Associates to remove product from cases #24 thru #30; wash down by 9:00 PM.

- Refrigeration Contractor to remove:

    - 32’ LM One-Deck Meat cases #24 thru #30 (A3)

- Deliver and Install:

- 32’ LSB Six-Deck meat cases N21, N22, N23, N24 (A3)

- All cases will be picked up by purchasing vendor.

- Plumbing Contractor must be on site to relocate the hub drains as required.

- General Contractor must patch and repair holes in the floor prior to the store opening.

- General Contractor must have the area cleaned up and safe for the public prior to leaving the site

Wednesday, February 26th (Day)

- Fresh Merchandising Specialist to be on site to assist the Store Personnel to merchandize product from removed cases.

Wednesday, February 26th (Night)

- Store Associates to remove product from cases #18 thru #21; wash down by 9:00 PM.

- Refrigeration Contractor to remove:

    - 28’ Single-Deck Meat cases #18, #19, #20 (A9)

    - 12’ LMDL Multi-Deck meat case #21 (A8)

- Deliver and Install:

- 28’ LSB Six-Deck meat cases N15, N16, N17 (A8)

- (3) BILBAO meat promos N18, N19, N20 (B4)

- All cases will be picked up by purchasing vendor.

- Plumbing Contractor must be on site to relocate the hub drains as required.

- General Contractor must patch and repair holes in the floor prior to the store opening.

- General Contractor must have the area cleaned up and safe for the public prior to leaving the site

Thursday, February 27th (Day)

- Deliver:

- Carlson Air Flow Shelving (Hold for Reset)

Monday, March 2nd (Night)	                                                                         PRODUCE CASE CHANGE OUT

- This is a lot of work so will need to start earlier than normal each night this week.  "BIG NIGHT"

- Store Associates to remove product from Produce cases #13 thru #17; wash down by 8:00 PM.

- Refrigeration Contractor to remove:

    - 12’ O5DM Multi-Deck cases #13 (A11)

    - 28’ QHZVP1 Single-Deck cases #14, #15 and #16 (A11)

    - 4’ Floral case #17 (A11)

- Deliver and Install:

- 4’ PF Floral case N08 (A11)

- 20’ DX6LN Wet Produce cases N09, N10 (A11)

- 12’ DX6LN Multi-Deck Produce case N11 (A11)

- 16’ DX6LN Multi-Deck Produce case N12, N13 (A9)

- 12’ DX6LN Multi-Deck Produce case N14 (A9)

- Plumbing Contractor must be on site to relocate the hub drains as required.

- General Contractor must patch and repair holes in the floor prior to the store opening.

- General Contractor must have the area cleaned up and safe for the public prior to leaving the site

Tuesday, March 3rd (Day)

- Fresh Merchandising Specialist and Store Associates to reset Produce Cases.

- Deliver and Install:

- JSI Tables for Produce.

- Fresh Merchandising Specialist to be on site to assist the Store Personnel in receiving the JSI tables and setting in place.

- Electrical Contractor must have telepoles on site.

Thursday, March 5th (Day)

- Décor Vendor to install Produce Pricing Kits

Monday, March 9th (Night)                                                                                   DELI / BAKERY SUSPENED

***Deli Bakery to suspend operations for renovations until March 25th ***

- General Contractor to remove a section of ceiling tile/grid in the Deli min. 8’ from the back wall and 16' wide for the removal of the existing Rack Oven and the installation of the new Rack Oven.  This is to include relocation of sprinkler heads that may be in this area.

- Store Associates to remove product from cases #1 thru #9 and Hot Deli case; wash cases by 9 pm.

- Refrigeration Contractor items being removed:

  - Wedge case #2 (A17)

  - Wedge case #5 (A5)

  - Wedge case #8 (A5)

  - 16’ LLM Service Cold Deli cases #4 and #6 (A15)

  - 8’ ED-72 Hot Deli

  - Rack Oven

- Refrigeration/Electrical/Plumbing Contractor to relocate: (temp for Deli product during Deli renovation)

- (2) 8' L4MG Self-Service cold deli case #1 and #3 (A17)

- (2) 8’ LSSD Self-Serve refrigerated bakery cases #7 and #9 (A14)

- General Contractor to dispose all removed cases.

- General Contractor to discard bread workstation.

- General Contractor to install a dust screen from the Deli canopy to the floor.  Drop clothes are acceptable.

- SESCO to deliver new Deli Hood.

- General Contractor to remove a section of ceiling tile/grid in the Deli min. 4' in front of the Hood for the removal and installation of the Hood system. This is to include relocation of sprinkler heads that may be in this area.

- Electrical Contractor to provide power to the scale location outside the dust screen.  Scale is wireless and can be moved by D/B Manager, Superintendent or FL Construction Supervisor.

- General Contractor must have the area cleaned up and safe for the public prior to leaving the site.

Tuesday, March 10th (Day)

- Operations to merchandise the 36' of temp cases #1, #3, #7 and #9 for refrigerated Deli and Bakery items during the Deli renovations.

Tuesday, March 10th (Night)

- Mechanical Contractor to begin removal of existing hood and the installation of the new Hood.  The new Hood is to be installed completely by the end of this week.

- General Contractor to have the infrastructure for the new Rack Oven complete this week.  This includes drain, electrical wiring and breaker, and hood ventilation.

- General Contractor/Plumbing Contractor to begin saw cutting for case drains/refrigeration/electrical.  Use plans marked up by Energy during the Preconstruction meeting.  All new refrigeration pits are to be fiberglass and completely sealed with spray foam, verify any existing concrete pits being reused have concrete bottoms.  All Electrical, Plumbing, and Refrigeration infrastructure for the new Deli Case lineup is to be complete by the end of this week.

Wednesday, March 11th (Day)

- General Contractor to contact Rick Thomas with SESCO (704-243-3811 office or 704-906-5244 cell) to coordinate the proper procedure of Fire Hood Test prior to Fire Marshall’s scheduled test.

- General Contractor to begin scheduling inspections for the new Deli Hood.

- Building Inspector to be scheduled for Monday for Hood Duct Weld inspection as required by local authorities.

- Fire Marshall to be scheduled for Wednesday morning for Hood Fire Alarm Testing as required by local authorities.

- Health Inspection to be scheduled for Thursday morning to inspect the Deli prior to opening as required by local authorities

Thursday, March 12th (Day)

- General Contractor and Mechanical Contractor to conduct their own “Light Test” on the welded duct to reduce delays during Monday’s inspection.  Results are to be communicated to the Construction Supervisor.

Monday, March 16th (Day)                                                                                    D/B EQUIPMENT DELIVERY

- Building Inspector to conduct a Duct Weld Inspection as required by local authorities.

- General Contractor must have the Deli professionally cleaned by Thursday of this week ahead of any Health Department Inspection.

- Deliver/Install:

- SHO-E Convection Oven. (Refrigeration Contractor is to install all equipment)

- Photo Cake Printer

- (2) Eye Wash (Deli and Meat Prep)

- LRO-1E4 Rack Oven (Refrigeration Contractor to unload and place oven in the Deli for installation by vendor)

- Electrical Contractor must hook up the equipment as soon as it is installed.

Monday, March 16th (Night)

- Refrigeration Contractor to have all refrigeration piping roughed in for new Deli case lineup.

- General Contractor to have ceiling grid/tile work completed around the new Rack Oven and Hood.

- Store Associates to remove product from cases #1, #3, #7, #9 and #10, wash cases by 9 pm.

***Cases may take (2) nights to install***

- Refrigeration Contractor items being removed:

  - (2) 8' L4MG Self-Service cold deli case #1 and #3 (A17)

  - (2) 8’ LSSD Self-Serve refrigerated bakery cases #7 and #9 (A14)

  - 3 Door L5FG Frozen Bakery case #10 (B2)

- Deliver/Install:

- (2) 12’ PT-72 Cold Deli case N01, N02 (A17)

- (2) 8' PT-54 Self- Serve cold Deli cases N03, N05 (A17)

- 12' PTD-54 Service Deli case N04 (A17)

- 8' PT-54 Self- Serve Bakery case N06 (A17)

- 4 Door QIV5V14 Frozen Bakery case N07 (B2)

- 6' PF-6HC-54 Hot Deli

- 5’ MHFC6044M-FF Hot Wing Bar

- Electrical Contractor must hook up the equipment as soon as it is installed.

- Electrical Contractor to attach the new sensor cables to cases, run to rack and have ready to terminate.

- General Contractor must patch and repair holes in the floor prior to the store opening.

- General Contractor must have the area cleaned up and safe for the public prior to leaving the site.

Tuesday, March 17th (Day)

- Vendor to un-crate the Rack Oven and set in place.

- Electrical Contractor/ Plumbing Contractor to make connections to Rack Oven.

Wednesday, March 18th (Day)

- Deliver and Install:

- JSI Tables for Deli/Bakery.

- Fresh Merchandising Specialist to be on site to assist the Store Personnel in receiving the JSI tables and setting in place.

- All old Deli/Bakery tables will be picked up by purchasing vendor.

Wednesday, March 18th (Night)

- Electrical Contractor to have power in place for all slicers and scale power in place by the end of tonight.

Thursday, March 19th (Day)

- General Contractor must have the Deli professionally cleaned

- Health Inspection as required by local governing authorities.

- Misting System Vendor to be on site to install misting system at Produce case

Thursday, March 19th (Night)

- General Contractor to remove dust wall and make area safe for public.

Monday, March 23rd (Day) 	                                                                         DELI RESUMES OPERATIONS

- Operations to merchandise new Deli Cases once all inspections have passed.

- Deli Associates to receive training on new Convection Oven.

- Vendor to startup and test the new Rack Oven.

- Salcoa to install the new NexGen and LP cabinets.

Wednesday, March 25th (Day)

- Deli Bakery to resume full operations.

Thursday, March 26th (Day)

- Deliver:

- Grocery shelving  (Hold for install)

Sunday, March 29th (Night)	                                                                                           GROCERY RESET

****Begin Grocery Reset****

- Delhaize America Vendor is responsible for disposal of the old gondola shelving. Set Team will be responsible for getting it to the dock area.

- The General Contractor’s Superintendent is to be on site 7:00 pm to meet with the Store Set 
Supervisor to discuss this week’s work.

- Note: All ceiling tile work must be done after the final grocery reset

Monday, March 30th (Night)

****Store will close at 9:00 pm****

- Grocery Reset Continues!

Tuesday, March 31st (Night)

****Store will close at 9:00 pm****

- Grocery Reset Continues!

Wednesday, April 1st (Night)

****Store will close at 9:00 pm****

- Grocery Reset Continues!

- Deliver and Install:

- New Endcaps.

Thursday, April 2nd (Night)

****Store will close at 9:00 pm****

- Grocery Reset Continues!

- Décor Vendor to install aisle markers

Monday, April 6th (Night) 	                                                              START RESTROOMS/ DEMO DECOR

- Electrical Contractor and General Contractor - to start CR and OW Panels and front wall renovation finishes and electrical with cat5.  Must be complete this week.

- General Contractor to begin Restroom renovations, working one restroom at a time.  Must be complete by April 24th.

- General Contractor to begin demo of existing décor and painting the walls.  Must be complete by April 24th.

Wednesday, April 8th (Day)

- Sign Vendor to install new store front sign and road signage

Friday, April 10th (Day)

- Electrical Contractor/General Contractor to have all front wall and office renovations finishes complete and electrical ready. To have all circuits relocated and cat5 ready for install.

Sunday, April 12th (Night)                                                                             NEXGEN CABLING/ START VCT

- Flooring Contractor to begin removing VCT and patching the floor.  This will be a (4) week process to complete new VCT installation.  To be complete by May 8th with store closing at 10pm.

Monday, April 13th (Day)

- Deliver:

- New Front end shelving.  (Hold for install on April 22nd)

Wednesday, April 15th (Night)

****Store to close at 9pm tonight and re-open at 7am****

- Store to have at least 25 pallets for the front end install

- Remove:

- (7) existing checkouts

- Tobacco Kiosk and gate w/2 checkouts.

- Deliver and Install:

- (6) Royston checkouts.

- (1) Tandem Checkout

- (1) 8’ R326 Counter

- (2) TAC-14GS Grab-N-Go’s

- Cigarette cabinets

- Baby Formula cabinet

- Front Office Cabinet  (GC to install)

- General Contractor to remove old Customer Service counter at front of store.

- General contractor to have counters and shelves re-laminated/modified prior to install of equipment.

- Macro to terminate all front wall cat5 for lotto, coinstar, western union.

- Mid-Carolina to make the check stand revisions.

- General Contractor to dispose of the removed check stands.

- Mandatory 9:00 pm meeting with MIS (Macro Integration Services) and Mid-Carolina Electric to discuss tonight’s work.  Everyone’s cooperation is respectfully requested.

- Salcoa will build / level the frontend shelving.

- Mid-Contractor is to provide pull strings for Muzak.

- Registers must be operational by at 7 am.

- Electrical Contractor/General Contractor to have all front wall renovations finishes complete and electrical ready. To have all circuits relocated and cat5 ready for install.

- Note: Clean power is to be ran to all PC’s (with orange receptacle)

Thursday, April 16th (Night)

- Décor Vendor is to install new lane lights.

- Muzak to be on site to install microphones on registers, DSD and speakers in offices as required.

- Deliver:

- (29) Case Corner Guards

Sunday, April 19th (Night)                                                                          NEXGEN CABLING/ VCT CONT’D

- NEXGEN cabling by vendor (Watcher) is to take place this week. This work will take place at night, Sunday through Thursday and will consist of pulling cables overhead throughout the store using a lift.  There should be no Power shutdown, Grocery Reset, Electrostatic Painting or Strip/Wax taking place this week.

- Flooring Contractor to continue flooring.

Monday, April 20th (Day)

- Deliver/Install:

- (3) Cart Corrals signage only.

- (4) Hand Dryers

- (5) Toilet paper dispensers

- (2) Bug Zapper (Grocery storage and Janitor area)

- (1) K-Cup Machine

- (1) Refrigerator

- (1) Stainless Steel Table

- (6) Lockers

- (3) DMO Chairs

Friday, April 24th (Day)

- General Contractor to be complete with restrooms.

- Painting Contractor to be complete with the Sales area and Office painting.

Sunday, April 26th (Night)                                                                       GONDOLA MOVES/ START DECOR

- Gondola Moves to begin to replace VCT under the gondolas.

Monday, April 27th (Day)

- Décor Vendor to begin 2 Weeks of Décor install:  Wall graphics, Trellis and valances to be installed. Complete by May 8th.

Tuesday, April 28th (Night)

- Décor Vendor to install Trellis

- Electrical Contractor to be on site to power up the Produce Trellis

Monday, May 4th (Day)                                                                                                                     PORTICO

- General Contractor to have Portico set-up to install new Vestibule carpet.  Visible signs will need to be posted so customers can see what door to use.

- Crescent Plumbing to perform a complete drain inspection on the store's sanitary sewer system.  General Contractor/Plumbing Contractor to work to complete any items discovered prior to Crescent's scheduled follow up visit

Friday, May 8th (Day)

- Flooring Contractor to have VCT complete.

- Décor Vendor complete.

- Remodel Substantially Complete.

Monday, May 11th (Day)                                                                        ELECTROSTATIC PAINTING/ SESCO

- Project Manager and Job Superintendent “MUST” punch the store and provide a completion list to the Food Lion Construction Supervisor.

- SESCO to perform the punch list with their Energy Management Team and Test/Balance Sub.  The General Contractor must communicate to all subs are to be present at the time of SESCO’s inspection. Please coordinate with Billy McCollough 336-580-0152

Monday, May 11th (Night)

- Electrostatic Painter to paint cases as needed.  Due to the scheduling of this work, the Electrostatic Painting may take place at any time during this week.  Notification will be made once firm date is set. Vendor will provide air scrubbers. Air scrubbers are to be left running on the sales floor until 8:30am. Do not shut off HVAC air handlers. (2 - day process)

Sunday, May 24th (Night)                                                                              STRIP AND WAX/ PUNCH WALK

- Strip and wax floors. (This is a 2 night process)

Monday, May 25th (Day)

- Construction Manager to coordinate with the Retail Specialist, Project Manager and Superintendent to write the punch list.  Retail Specialist is to attend and generate their Construction Completion Assessment.

- General Contractor must complete this punch list by the End of Scheduled Construction Activity date.

- SESCO to forward their punch list to the Construction Supervisor and the General Contractor.  SESCO will perform a final inspection in 2 weeks. Make sure all items are complete prior to re-inspection to avoid additional trip charges.

- General Contractor must have ALL final inspections complete and obtain a CO.

General Contractor to contact TBD to have the Coinstar re-installed in new location today

Friday, May 29th (Day)

- Electrical Work Deadline – Electrical Contractor to be complete with all electrical items found in bid notes and on plans by today in preparation of the Electrical Commissioning scheduled for next week.  Contact Crescent Construction (704 633 9697) for courtesy call from Crescent Technician prior to arrival.  Additional inspections and associated fees may result by not being ready on this date.

Monday, June 1st (Night)                                            END OF CONSTRUCTION/ CRESCENT ELECTRICAL

- Crescent Construction to perform electrical commissioning report this week.

- Energy Team will conduct a complete store RCC, General Contractor to complete any items as soon as the report is available.

- Note: Sylvania must come in one week prior to completion for light bulb change out.

- Coinstar to be re-installed this week.

Friday, June 5th (Day) ***End of Scheduled Construction Activity (technical punch continuation)***

- General Contractor must submit all final change orders by this date.

Friday, July 3rd (Day/Night)                                                                                  TECHNICAL PUNCH LIST

- General Contractor and Subs complete Technical Punch List.

Construction Manager: Chad Lowder

1458schdraft