March 17, 2020

# RE:		FOOD LION STORE #1662 Laurel, MD - REMODEL SCHEDULE

NOTE: Grocery Reset to take place the week of April 26th, 2020.  General Contractor will not be     involved in this procedure.

Week #1

Mobilization/Pre-Con Meeting/Begin Backroom

Monday, July 13th (Day) w1

- General Contractor to verify that all subs have ordered ALL equipment for the remodel.  Delays 
will not be tolerated. Provide the Construction Manager proof of order for all of the General 
Contractor’s and Sub’s equipment/supplies at the Preconstruction Meeting.

- General Contractor to mobilize this week, including delivery and installation of storage containers and dumpsters.

- Loss Prevention to have a camera focused on the designated construction door and all exit doors.

- General Contractor is responsible for providing supervision for all contracted work.  The General Contractor shall split day and night shifts between a lead Carpenter and the Job Superintendent when night work is scheduled.

Note:  All the incoming construction related materials must be staged in the RED ZONE and the Bill of Lading placed in the office notebook for the General Contractor's review each day.

Note: General Contractor may install a pull handle on the outside construction dumpster access door and this door must remain closed at all times if it is decided the dumpster will be behind the store.

Note:  General Contractor to record existing condition of entire store inside and out by digital photo or video.

Note:  All scissor lift operations must have a spotter on the floor for safety at all times (during any daytime work).  This is not required during night work.  When not in use and left on the sidewalk; lift(s) must be covered in orange construction fencing.  If this is not adhered to, lift(s) will be required to be stored away from front sidewalks.

Reminder:  General Contractor must coordinate any night coverage with the Store Manager no later than Wednesday prior to the coming week every week.

-	General Contractor to begin the bid note/Plan items work in the Dept. Manager's Office/PC Training and other backroom areas.

NOTE: Make sure counter and shelf are pre-ordered before construction begins.

- Electrical Contractor to support GC in DMO/PC Training Room.  All electrical and data in DMO/PC Training Room are to be completed prior to Front End Set.

- General Contractor to remove Humidifier System in Produce Prep to allow ProDew to install polyboard next week.

Tuesday, July 14th (Day) w1

- Pre-construction Meeting Today - between the Store Managers, Deli Lead, QA and PIC Associates, General Contractor, Construction Manager and Retail Specialist.  MUST BE PRESENT at 2:00 pm.

- General Contractor to verify that all subs have ordered ALL equipment for the remodel.  Delays 
will not be tolerated. Provide the Construction Manager proof of order for all of the General 
Contractor’s and Sub’s equipment/supplies at the Preconstruction Meeting.

- General Contractor must have a 24 Hour contact list present to give to the Store Manager. 
Please keep this list in the Notebook.

- General Contractor to install Safety Rail Kits to the tops of all walk-ins and Backrooms per instructions as required. These must be installed as soon as delivered.

- Note: SE Retail has determined there is “NO” future décor issues that the fire alarm equipment that will need to be relocated.

- Energy Specialist to adjust "work light relays" for any scheduled night work.

- General Contractor is to contact Sheila Hyde, SLHyde@foodlion.com to schedule the Coinstar to be “RELOCATED” on August 12th.

Wednesday, July 15th (Day) w1

- Deliver: (GC to uncrate, assemble and install all items upon receipt)

  - (2) Bug Zappers for Backroom

  - Eye Wash for Janitor Room

  - Traffic Doors (GC to order)

Week #2

DELI/PRODUCE

Monday – Thursday, July 20th – July 23rd (Day and Night) w2

- General Contractor and Sub Contractors to continue with bid note and plan items this week. This is both Day and Night work.

- General Contractor is to remove sign this week and begin preparing EFIS surface and painting of storefront – complete within (3) weeks.  Use Sign Banner provided by Construction Manager mounted on frame (as described in Walk Notes).

Monday, July 20th (Night) w2

- General Contractor is to remove and dispose of Deli fillers and 8’ Bread Workstation.

- General Contractor is to begin work on New Partial Height Wall in Deli.  Make sure appropriate measures are taken in covering up existing Deli Cases, etc. to prevent dust issues each night of work here.

- General Contractor is to begin demo of Customer Service Counter/Wall/Gate and removal of designated marlite in same area this week.

- Electrical Contractor is to support GC in these areas.

- General Contractor must have the area cleaned up and safe for the public prior to leaving the store each night.  Use orange cones.

- General Contractor/Painting Contractor to begin removal of existing sales area décor and painting the walls.  Walls must patched/skimmed, sanded, and wiped down with a damp sponge/cloth to remove dust.  Walls must have a Level 4 finish.

- General Contractor to provide pictures of paint can labels for Construction Manager and is to manage this process.

- Final coat on doors and frames is suggested to be completed later in the project.

- NOTE: Have all wall painting completed prior to Décor install.

- General Contractor to manage the PIC Safety sheets for this project as described at the Precon for all night work shifts.  GC to maintain nightly signed Safety Sheets and must be turned over to Construction Manager at the end of the project.  NOTE: Begins Tonight.

Tuesday, July 21st (Day) w2

- Deliver:

  - Carlson Air Flow

  - ABS Shelf Stop

Wednesday, July 22nd (Day) w2

- Prodew to install poly board in Produce Prep rough-in pex for new Misting System.

Thursday, July 23rd (Day) w2

- Produce Fresh Lead and Produce Associates to merchandise existing Produce Cases.

- Deliver/Install: (approx. 8 – 10 a.m., Strategy Specialist to assist store in unloading and checking for damaged items)

- Banana Table

- Deliver:

    - Deli Auto Slicer

    - Deli Slicer Stand

- Décor Vendor to install produce sign kits (product pricing kits).

Week #3

Backroom Cont./Front Wall/Workroom

Monday, July 27th (Day) w3

- General Contractor and Sub Contractors to continue with bid note and plan items this week.  This is both Day and Night work.

- Store Manager to work to remove items from shelving and counter in front office that is being removed.  Coordinate with General Contractor.

- Store Manager to work to empty the outer office area at the front end to allow General Contractor to Demo work.  Coordinate with General Contractor.

-	Electrical and Plumbing Contractors must have rough in for Produce Case Misting System complete this week.

Monday, July 27th (Night) w3

- General Contractor is to begin work in Workroom this week.

- Electrical Contractor to support GC in Workroom.

- General Contractor to adjust front end equipment as needed to accommodate relocations.

- Electrical Contractor to begin installation of all CAT5, phone lines, all front wall electrical and power for the front end/customer service area complete prior to Front End Set.

Week #4

Front Wall/Workroom cont./Misting System

Monday, August 3rd (Day) w4

- General Contractor and Sub Contractors to continue with bid note and plan items this week. This is both Day and Night work.

- General Contractor to be complete with EIFS storefront 100% this week to prepare for sign install next week.

- General Contractor to continue with bid note and plan items this week.

Monday, August 3rd (Night) w4

- Painting Contractor to complete the Sales Area painting this week.

Tuesday, August 4th (Day) w4

- Construction Manager and General Contractor to inspect the water and power for the misting system to ensure everything is ready.  General Contractor to provide digital photo of the water/power.

Wednesday, August 5th (Day) w4

- Misting System to be installed by Vendor as shown on plans for Produce cases.  Produce Associates to assist the installer with product removal in the wet cases in order for installer to mount system to shelving.

Week #5

SIGN INSTALL/Coinstar

Monday, August 10th (Day) w5

- General Contractor and Sub Contractors to continue with bid note and plan items this week.  This is both Day and Night work.

- Store Manager is to ensure that 15 plastic pallets are retained for use during the Front End Check Stand work scheduled for next Wednesday night, 8/19.

- Deliver: (GC to uncrate, assemble and install all items upon receipt)

  - Refrigerator - Lounge

  - K Cup Coffee Maker - Lounge

  - Stainless Steel Table – Lounge

  - Table and chairs for Lounge

  - 3 chairs for DMO/PC Combo

Tuesday, August 11th (Day) w5

-	Sign Vendor to install new storefront sign and any road sign(s) this week.  Actual install date TBD.

-	Electrical Contractor is to ensure there is power to the new storefront signage and it illuminates.

-	Note:  Only ½ of the storefront entrance is to be closed or worked on at a time if needed for sign work.

Wednesday, August 12th (Day) w5

- CoinStar equipment is to be relocated by vendor (Contact Sheila Hyde, SLHyde@foodlion.com if the Coinstar is not relocated on this date.)

- Vendor to install new Fresh Maxx system In Produce Prep.

- Vendor to install Click and Clean in Produce Prep.

Week #6

FRONT END/DÉCOR(1)

Monday, August 17th (Day) w6

-	Décor Vendor is to begin installation of new Décor.  This will be a two week process and will require both day and night coverage.

- General Contractor to ensure all work listed in bid notes are completed as well as all work indicated in plans over the next two (2) weeks.

- Deliver:

  - Kiosk Shelving. Hold for set team for install with Front End Equipment.

Monday, August 17th (Night) w6

- General Contractor and Sub Contractors to continue with bid note and plan items this week. This is both Day and Night work.

Tuesday, August 18th (Day) w6

- General/Electrical Contractors must verify to Construction Manager that Electrical Contractor has all receptacles/Cat5 installed in PC Training, Department Managers Office and Front Wall in preparation for tonights' installations.

Wednesday, August 19th (Day) w6

- 7 pm Delivery: (store in backroom or Frozen Food aisle for installation tonight)

  - 4 Bagwell Ends

  - Workroom Cabinet

  - 72” Formula Cabinet

Wednesday, August 19th (Night) w6

FRONT END SET - Store to close at 9 pm tonight and open at 8 am on August 20th.

-	Front End Contractor Team to meet on site at 8 pm to discuss tonight’s work.

-	Remove/discard:

  - 4 Scan & Bag Ends

  - Cabinets along back.

-	General Contractor is to dispose of all Front End check stand ends and kiosk cabinets.

-	Front End Team to install all items listed above.

-	Relocate T&A Cabinet and Coupon Kiosk.

- Macro to make terminations on all installed CAT5 cables on the front wall (if required).

Thursday, August 20th (Day) w6

- Décor Contractor to install register lane lights.

- Deliver/Install:

  - Rug Doctor

- Relocate:

  - Ice Vendor

  - Primo Water Exchange

  - Coupon Kiosk

- General Contractor to set all front end equipment per layout on drawings.

- Deliver:

    - (16) Case Corner Guards (GC to install after case and floor work)

    - (3) Double Cart Corral Sign Headers

Thursday, August 20th (Night) w6

- Soft Tile Contractor to patch VCT floor tile, approximately 112 tile.  See Bid Notes for described areas and related number of tile for each location.

NOTE: If unable to install this night, they must install one night next week. Floor needs to set up a minimum of 72 hours before Strip and Wax.  I would prefer to set up as long as possible.

Week #7

DÉCOR(2)/PORTICO/NextGen Cabling

Sunday, August 23rd (Night) w7

- NextGen Cabling by Vendor (Wachter) is to take place this week.  This work will take place at night Sunday through Thursday and will consist of pulling cables overhead throughout the store using a lift.  There should be no Power Shutdown, Grocery Reset, Electrostatic Painting, or Strip/Wax taking place this week.

- Loss Prevention to begin installation of upgrade of the security camera system this week.

Monday, August 24th (Day) w7

- Décor Vendor is to complete installation of new Décor this week.

- General Contractor is to have Vendor install Vestibule carpet.  Close off only (1) one entrance at a time.  Protect work area with appropriate barricades.

- General Contractor to ensure all work listed in bid notes are completed as well as all work indicated in plans this week.

- Construction Manager to write Punch List this week.

Friday, August 28th (Day) w7    ***End of Scheduled Construction Activity***

- General Contractor must submit all final change orders by this date.

Week #8

ELECTROSTATIC PAINT

Monday, August 31st (Day) w8

- General Contractor to ensure all work listed on Punch List is completed as well as all work indicated in plans this week.

Monday, August 31st (Night) w8

- Electrostatic Painter to paint Meat, Lunch Meat and Promo Cases, Front End equipment, Dairy Cooler in Corridor and Deli Freezer/Cooler doors. Also Due to the scheduling of this work, the Electrostatic Painting may take place at any time during this week.  Notification will be made once a firm date is set.  Vendor will provide 5 sets of air scrubbers.  Air scrubbers are to be left running on the Sales floor until 8:30am.  Do not shut off HVAC air handlers.

- Store Associates – COOL Magnets and Décor Department signs must be left off of electrostatic painted cases for a minimum of 24 hours after painting is complete.  Otherwise it is likely the new paint will peel off when signs are removed.

STRIP/WAX

Monday, September 7th (Night)

- Strip and wax.  Note: This is a 2 night process.  It can happen any (2) nights this week.  You will be notified in advance to actual days.  Any changes to this date can only be made by the Construction Manager.

Any security or Loss Prevention problems should be brought to the attention of Jason Pethel, Jason.Pethel@RetailBusinessServices.com  (704-310-4248).

As discussed at the Pre-construction/Schedule Coordination meeting, it is imperative that the Temperature Log be kept current.  In the event a temperature problem is discovered, notify the Refrigeration Contractor and the General Contractor immediately.  It is also the Store Manager’s responsibility to notify the Construction Manager and the Maintenance Supervisor as soon as possible after a problem is discovered.

Again, any problems or concerns with the above schedule need to be directed to me.

Thank you in advance for your patience in the completion of this Renewal Project.

Sincerely,

BUILDING OUR FUTURE...

Alan Wilson

Alan Wilson

Construction Manager 1

AW/afw

1662schdraft