## G702
APPLICATION AND CERTIFICATION FOR PAYMENT |  |  |  |  | AIA DOCUMENT G702 |  |  | PAGE 1 OF |  | 2 | PAGES
TO OWNER: |  |  | PROJECT: | Food Lion 2250 |  | APPLICATION NO: 2 | 1 |  | Distribution to:
Delhaize | [5 empty] | Application Date: | 2020-02-25 |  | x | OWNER
PO Box 2487 | [9 empty] | ARCHITECT
X
2085 Harrison Road Salisbury 28145-2487 | [5 empty] | PERIOD TO: 02/29/2020 |  |  | x | CONTRACTOR
FROM CONTRACTOR:
Vertex Construction Company, LLC | [5 empty] | Invoice # 20003-1
721 Corporate Cir | [5 empty] | Purchace Order #
Salisbury NC 28147
[6 empty] | CONTRACT DATE:12/23/2015 | 2020-02-13
Construction Supervisor:
CONTRACTOR'S APPLICATION FOR PAYMENT |  |  |  |  | The undersigned Contractor certifies that to the best of the Contractor's knowledge,
Application is made for payment, as shown below, in connection with the Contract. |  |  |  |  | information and belief the Work covered by this Application for Payment has been
Continuation Sheet, AIA Document G703, is attached. |  |  |  |  | completed in accordance with the Contract Documents, that all amounts have been paid by
the Contractor for Work for which previous Certificates for Payment were issued and
payments received from the Owner, and that current payment shown herein is now due.
1. ORIGINAL CONTRACT SUM |  |  | $ | 815073
2. Net change by Change Orders |  |  | $ | 0 | CONTRACTOR: Vertex Construction Company, LLC
3. CONTRACT SUM TO DATE (Line 1 ± 2) $ |  |  | $ | 815073
4. TOTAL COMPLETED & STORED TO |  |  | $ | 216980
DATE (Column G on G703) |  |  |  |  | By: |  |  |  | Date: | 2020-02-25
5. RETAINAGE: |  |  | 21698
a. |  | % of Completed Work $ |  |  | State of: North Carolina |  |  | County of: | Rowan
| (Column D + E on G703) |  |  |  | Subscribed and sworn to before me this |  |  | day of
b. |  | % of Stored Material $ |  |  | Notary Public: | [5 empty] | .
| (Column F on G703) |  |  |  | My Commission expires: |  | 2020-06-28
Total Retainage (Lines 5a + 5b or
| Total in Column I of G703) |  | $ | 21698 | ARCHITECT'S CERTIFICATE FOR PAYMENT
6. TOTAL EARNED LESS RETAINAGE |  |  | $ | 195282 | In accordance with the Contract Documents, based on on-site observations and the data
| (Line 4 Less Line 5 Total) |  |  |  | comprising the application, the Architect certifies to the Owner that to the best of the
7. LESS PREVIOUS CERTIFICATES FOR |  |  |  |  | Architect's knowledge, information and belief the Work has progressed as indicated,
PAYMENT (Line 6 from prior Certificate) |  |  | $ | 0 | the quality of the Work is in accordance with the Contract Documents, and the Contractor
8. CURRENT PAYMENT DUE |  |  | $ | 195282 | is entitled to payment of the AMOUNT CERTIFIED.
9. BALANCE TO FINISH, INCLUDING RETAINAGE $ |  |  |  | 619791
| (Line 3 less Line 6) |  |  |  | AMOUNT CERTIFIED . . . . . . . . . . . $
CHANGE ORDER SUMMARY |  |  | ADDITIONS | DEDUCTIONS | (Attach explanation if amount certified differs from the amount applied. Initial all figures on this
Total changes approved |  |  |  |  | Application and onthe Continuation Sheet that are changed to conform with the amount certified.)
in previous months by Owner |  |  |  |  | ARCHITECT:
Total approved this Month |  |  |  |  | By: |  |  |  | Date:
TOTALS |  |  | 0 | 0 | This Certificate is not negotiable. The AMOUNT CERTIFIED is payable only to the
NET CHANGES by Change Order |  |  | 0 |  | Contractor named herein. Issuance, payment and acceptance of payment are without
prejudice to any rights of the Owner or Contractor under this Contract.
AIA DOCUMENT G702 · APPLICATION AND CERTIFICATION FOR PAYMENT · 1992 EDITION · AIA · ©1992 |  |  |  |  | THE AMERICAN INSTITUTE OF ARCHITECTS, 1735 NEW YORK AVE., N.W., WASHINGTON, DC 20006-5292
Users may obtain validation of this document by requesting a completed AIA Document D401 - Certification of Document's Authenticity from the Licensee.
Note: Items in RED FONT are automatically calculated from the G703 form or from items within this G702 Form. Do NOT hand enter these items on this sheet.

## G703
CONTINUATION SHEET |  |  |  | AIA DOCUMENT G703 |  | PAGE 2 |  | OF | 2 | PAGES
AIA Document G702, APPLICATION AND CERTIFICATION FOR PAYMENT, containing | [6 empty] | APPLICATION NO: |  | 1
Contractor's signed certification is attached. | [6 empty] | APPLICATION DATE: |  | 2020-02-25
|  |  |  | Food Lion 2250 |  |  | PERIOD TO: |  | 2020-02-29
Use Column I on Contracts where variable retainage for line items may apply. | [6 empty] | ARCHITECT'S PROJECT NO:
A | B | C | D | E | F | G |  |  | H | I | J
| DESCRIPTION OF WORK |  | WORK COMPLETED |  | MATERIALS | TOTAL | %
ITEM |  | SCHEDULED | FROM PREVIOUS |  | PRESENTLY | COMPLETED |  |  | BALANCE | RETAINAGE | THIS PERIOD
NO. |  | VALUE | APPLICATION | THIS PERIOD | STORED | AND STORED | (G ÷ C) |  | TO FINISH | (IF VARIABLE | LESS
|  |  | (D + E) |  | (NOT IN | TO DATE |  |  | (C - G) | RATE) | RETAINAGE
[5 empty] | D OR E) | (D+E+F)
010000 | General Requirments | 176931 |  | 58977 |  | 58977 | 33.33% |  | 117954 | 5897.7 | 53079.3
010001 | Epoxy Floor Allowance | 8000 | [6 empty] | 8000 | 0 | 0
010002 | Deli Stainless Steel Allowance | 3000 | [6 empty] | 3000 | 0 | 0
Site
312000 | Site Improvements | 775 | [6 empty] | 775 | 0 | 0
024116 | Interior Demolition | 22405 |  | 20000 |  | 20000 | 89.27% |  | 2405 | 2000 | 18000
030000 | Floors & Slabs | 3000 |  | 3000 |  | 3000 | 100% |  |  | 300 | 2700
042200 | Unit Masonry | 2500 |  | 1500 |  | 1500 | 60% |  | 1000 | 150 | 1350
050000 | Metals | 10760 | [6 empty] | 10760 | 0 | 0
Carpentry/Bulkhead
062000 | Carpentry | 15503 |  | 7500 |  | 7500 | 48.38% |  | 8003 | 750 | 6750
070000 | Thermal & Moisture protection | 14460 | [6 empty] | 14460 | 0 | 0
080000 | Openings | 150 | [6 empty] | 150 | 0 | 0
092000 | Plaster and Gypsum Board | 37705 |  | 15000 |  | 15000 | 39.78% |  | 22705 | 1500 | 13500
093000 | Ceramic Tile | 10000 | [6 empty] | 10000 | 0 | 0
095100 | Acoustical Ceilings | 21400 | [6 empty] | 21400 | 0 | 0
096500 | Resilient Flooring | 148528 | [6 empty] | 148528 | 0 | 0
099100 | Painting | 28976 | [6 empty] | 28976 | 0 | 0
100000 | Interior Specialties | 11780 | [6 empty] | 11780 | 0 | 0
210000 | Fire Sprinkler | 7000 | [6 empty] | 7000 | 0 | 0
220000 | Plumbing | 66250 |  | 29700 |  | 29700 | 44.83% |  | 36550 | 2970 | 26730
230000 | HVAC | 58200 | [6 empty] | 58200 | 0 | 0
260000 | Electrical | 167750 |  | 81303 |  | 81303 | 48.47% |  | 86447 | 8130.3 | 73172.7
| GRAND TOTALS | 815073 | 0 | 216980 | 0 | 216980 |  |  | 598093 | 21698 | 195282
Users may obtain validation of this document by requesting of the license a completed AIA Document D401 - Certification of Document's Authenticity