March 18, 2020

# FOOD LION STORE #2560 EDGEMERE, MD - REMODEL SCHEDULE DRAFT

Week 1

Monday July 6- DAY WORK

- General Contractor to mobilize this week, including delivery and installation of storage containers, dumpsters, and security fencing as described in the bid notes.

- Loss Prevention to have a camera focused on the designated construction door and all exit doors.

- General Contractor is responsible for providing supervision for all contracted work.  The General Contractor shall split day and night shifts between a lead Carpenter and the Job Superintendent when night work is scheduled.

- General Contractor to manage the PIC Safety sheets for this project as described at the Pre-con for all night work shifts.  General Contractor must maintain nightly signed Safety Sheets to be turned over to Construction Supervisor at the end of night work at the end of this project. This will be typical of ALL night work

- General Contractor to begin backroom items as listed in the bid notes and on construction drawings; including work indicated for Dept. Manager's Office, PC Training Room, Lounge and restrooms.

- General Contractor is to start working on the bid note items.

- Refrigeration Contractor to begin running new refrigeration lines.  Note:  Sales area refrigeration line work must be done at night unless authorized by the Construction Supervisor.

- General Contractor to contact Angie Walter (704-310-2328) to have ATM equipment serviced if bolts are needed to be removed.  General Contractor to remove ATM, place on pallet, shrink wrap, mark “DO NOT REMOVE FROM STORE”, and place in a safe/secure location in the back room.

- Note:  Refrigeration Contractors are required to keep the refrigeration lines on top of the cases towards the back to allow for valences and up-lighting. Coordinate location of new and relocated lines with the Superintendent and Construction supervisor.

- Note:  All the incoming construction related materials must be staged in the RED ZONE and the Bill of Lading placed in the office notebook for the General Contractor's review each day.

- Note: General Contractor may install a pull handle on the outside construction dumpster access door and this door must remain closed at all times if it is decided the dumpster will be behind the store.

- Note:  General Contractor to record existing condition of entire store inside and out by digital photo or video.

- Note: General Contractor must install chain-link fencing with privacy screen around the construction staging area. General Contractor must coordinate through the Construction Supervisor the location allowed for the construction zone.

- Note:  All scissor lift operations must have a spotter on the floor for safety at all times (during any daytime work).  This is not required during night work.

- Note:  Electrical Contractor is to wait until Décor Contractor is complete with décor before installing up-lighting.

- Reminder:  General Contractor must coordinate any night coverage with the Store Manager no later than Wednesday prior to the coming week every week.

- NOTE TO DEPARTMENT MANAGERS:  During Case moves, it is vital that you plan ahead with labor that will be needed to pull your cases.  Please use this schedule, the color coded drawings, and the tags on the cases left by the Refrigeration Contractor that will instruct you on when your cases will be removed or relocated.  NOTE: Not all cases in this store will be relocated, removed, or replaced.

- NOTE TO GC and ALL TRADES: This store has an accelerated Deli Schedule.  This means Deli work is to be 7 Days a Week once Started.  To facilitate this, it’s imperative that any Roof Top work for new curbs and fans is completed PRIOR TO the Deli Beginning.  Please plan your manning accordingly so there is adequate coverage for both day and night shifts during the Deli Remodel.

- General Contractor to contact JASON PETHEL to schedule the disconnect of the fire alarm from the Ansul hood in the deli following the close of the deli.

- General Contractor to contact Rick Thomas with SESCO to schedule the removal of the Fire Suppression Tank from Hood next week after all use of existing hood is complete.  Also, communicate to Jason Pethel the Ansul Reconnections and Fire Alarm Testing.  Jason Pethel will coordinate Food Lion’s Fire Alarm Contractor for these activities but needs a one week notice.

- General Contractor to coordinate with inspection department and SESCO on the need for a performance test

Tuesday July 7- DAY WORK

- Pre-construction/schedule Coordination Meeting between the Store Personnel, General Contractor (Project Manager and Superintendent), Refrigeration Contractor, Energy Team and the Retail Specialist.  All MUST BE PRESENT at 10:00 AM.

- Store Manager must have an area set up for approximately 20 people in the backroom.

- General Contractor to verify that all subs have ordered ALL equipment for the remodel.  Delays will not be tolerated. Provide the Construction Supervisor proof of order for all of the General Contractors and Sub’s equipment within the next two weeks.

- General Contractor and Construction Supervisor to walk the store for future décor issues that will need to be handled prior to the two week décor install.  Contact Aaron Ashely @704-310-3128 for fire alarm equipment that will need to be relocated and a designated time frame.

- Construction Supervisor, Energy Manager, Maintenance Supervisor, Refrigeration Contractor and General Contractor to review plans for hub drain and pit locations.

- IMPORTANT:  FOR ALL CASE MOVES DURING THIS REMODEL, CASES TO BE EMPTY and WASHED BY 9PM on the night of the case move.

- NOTE: GC is General Contractor, EC is Electrical Contractor, RC is Refrigeration Contractor

- NOTE: FOR ALL CASE MOVES, the EC WILL BE REQUIRED to have the sign off sheet complete by the Energy Supervisor.  Failure to do so will result in the EC being called back into the store to complete the work from the night before.

- GC, EC, and RC to work remainder of the week to prepare for Case Moves Next Week.  Cases will be moving in the Meat Department and ONE in Dairy next week.

- NOTE NOTE NOTE: FOR THIS MARKET,THE GC WILL BE RESPONSIBLE FOR REMOVING AND RECYCLING CASES.  ENSURE THAT YOU HAVE A FORKLIFT OR LULL THAT’S CAPABLE OF MOVING THESE CASES ON SITE FOR THE DURATION OF THE CASE MOVES.

- DELIVER Ice Cream Freezer Evaporator

- GC to begin working on infilling Meat Department Windows.  Meat Department Cases will install on Week 5.

- HBC Cage to Deliver.  Store to transfer HBC Items to Cage after Grocery Reset

Week 2                                                                                                 GROCERY RESET WEEK

Sunday July 12 THROUGH Thursday July 16- NIGHT WORK

- Grocery Reset.  Store to close at 9pm each night through Wednesday.

- General Contractor to have dumpster on site for shelving disposal.

- FOOD LION Vendor is responsible for disposal of the old gondola shelving. Set Team will be responsible for getting it to the dock area or front door.

- General Contractor’s Superintendent is to be on site 7:00 pm to meet with the Store Set Supervisor to discuss this week’s work.

- General Contractor to assist in securing wall shelving as needed.  GC TO PROVIDE 1X TO SECURE SHELVING AS NEEDED.

- Note: General Contractor will need to remove some signage as directed BY Operations and Reset Team.

- Note: Electrician may be needed to remove old floor outlets that were covered by Gondolas.  These need to be removed and capped under the floor.

- GC and EC to work on Backroom Items and Cash Office.  Office MUST BE READY by Week 10.

- GC to install New Bumper in Dairy Cooler L3x3x1/4 as shown on plans.

- GC to relocate Ice Machine tonight and place on 4x4s.

- Plumber to work on Ice Cream Line-Up as needed prior to Case install on Week 5.

Thursday July 16- Day Work

- Décor Company to install new Aisle Markers

Week 3                                                                                                                     DELI BEGINS

Sunday July 19-Night Work   ***NOTE: DELI WORK IS TO BE 7 DAYS A WEEK***

- Deli Personnel to pull product from cases 5, 6, and 7.  Wash and EMPTY BY 9PM.

- RC and GC to remove Cases 5 and 10’ Hot Deli and Recycle.

- RC to temporary set and install Cases 6 and 7.  May need to slide down to allow customer access to Case 8   Cases to be operational by 8am.  These cases to be outside of the dust wall that the GC is to install.

- General Contractor to start any Underground work as needed.

- General Contractor to remove a section of ceiling tile/grid in the Deli min. 4' in front of the Hood for the removal and installation of the Hood system.  This is to include relocation of sprinkler heads that may be in this area.

- Move all equipment including sinks from the Deli Bakery to a storage trailer while we are working in the Deli to give adequate space. This does not include the rack oven.

- General Contractor to install a dust screen from the Deli canopy to the floor.  Drop clothes are acceptable.

- Electrical Contractor to provide power to the scale location outside the dust screen.  Scale is wireless and can be moved by D/B Manager, Superintendent or FL Construction Manager.

- GC to remove the wall tile at the hood location and install sheetrock in area where the new hood installs.

- General Contractor must have the area cleaned up and safe for the public prior to leaving the store

Monday July 20- Day Work

- Deli Specialist to Temporary Set Cases 6 and 7.

- Day and Night Work is Authorized in Deli once Dust Wall is in place.  EXCEPTION: FLOOR CUTTING TO BE DONE AT NIGHT

- Plumber to install new Eye Wash and New Hand Sink once all drain work in the deli is complete.

- Mechanical Contractor to remove the hood and welded duct work if applicable and hang the NEW  13’ hood and start on the required duct work.

Monday July 20- Night Work

- GC labor to continue with hard tile removal and new sheetrock installation as needed.

- Remove the wall grid as tile is removed.

- Electrical work in the walls and overhead is to commence tonight. The circuits at the hood area is priority.

Tuesday July 21- Day Work

- The welded ductwork is to be completed today and the light inspection for this is to be scheduled for the following day in advance.

Tuesday July 21- Night Work

- Slab infrastructure is to be completed tonight and ready for inspections the following day.

- Electrical work in the walls and overhead is to complete tonight and be ready for inspections.

- Finalize any tile removal and new sheetrock added.

Wednesday July 22- Day Work

- Inspections on the welded ductwork for the hood, new in the wall/overhead electrical, and slab infrastructure work to be scheduled today.

Wednesday July 22- Night Work

- Closeup the ceiling around the hood, and finalize any sprinkler work and complete any lighting adds/relocations etc.

Thursday July 23- Day Work

- Wall ceramic work is to start today.

Thursday July 23- Night Work

- Deliver and Install New BLFF-208 72 PC Fryer, New Convection Oven, and Auto Slicer

Friday July 24- Day Work

- Wall ceramic will complete today.

- Fire Alarm, Ansul added to hood today, with pretest to follow.

Friday July 24- Night Work

- Finalize any of the work above that is incomplete.

Saturday July 25- Day Work

- Reinstall all sinks, tables processing equipment and the new eye wash stations.

- Tie the ceiling back in to the new wall tile.

Week 4                                                                                  Deli Cases Arrive and Deli Finish

Sunday July 26- Night Work

- GC to remove Dust Wall tonight prior to Cases being installed.

- Store Personnel to Pull Product from Deli Cases 1, 2, 3, 4, 6, 7, and 8.

- RC to remove Cases 1, 2, 3, 4, 6, 7, and 8.  GC to Salvage.  HOLD CASE 2 IN BACK ROOM.

- RC to receive and begin installing 24’ DX6LN (N63/64 A13), 6’ Hot Deli, 16’ PT-54, 8’ PTD-54, 6’ PT-72, 6 Doors QIV5V14 Frozen Bakery, 5’ Wing Bar, and 2’ HSC Single Deck Deli

- NOTE:  RC may take 2 Nights to install these cases.

- EC to have Power ready to be dropped for Wing Bar and 2’ Deli Case

Monday July 27- Night Work

- Finalize any details on the case installation.

- Professionally clean the Deli Bakery, all sub-contractor work is to be finalized prior to tonight without exception.

- GC to make slab repairs where Case 8 was located.

Tuesday July 28- Day Work

- If Allowed to by the Health Department, we will stock the new cases. If not the Health Inspector is to be pre-scheduled for today to inspect for temp checks. This is to be determined in advance.

- Schedule the final Hood, Electrical, Plumbing inspection, today.

Tuesday July 28- Night Work

- All inspection items to be completed tonight.

- Final trim out issues to be completed tonight.

Wednesday July 29- Day Work

- Deliver the new Wooden Deli JSI Merchandising fixtures. The Deli Specialist will be on site to receive and merchandise.

- Equipment training today on New Fryer and Convection Oven

Thursday July 30- Day Work

- Deli to be completely Re-Opened today.  If for some reason the Deli cannot open toay, Move this Opening Day to Friday.

WEEK 5                                          Dairy, Ice Cream and Frozen Departments

Sunday August 2- Night Work

- Store Personnel to pull product in Dairy Cases 31 THROUGH 37.  Cases to be empty and washed by 9pm

- RC to relocate Dairy Cases 31 THROUGH 37.

- GC to work on DMO Office now that its available.

Monday August 3- Day Work

- Ice Cream, Frozen, and Dairy Reset to Begin Today.  Reset Cases 31 THROUGH 37.

Monday August 3- Night Work

- Store Personnel to pull Product from Ice Cream Cases 38, 39, 40, and 41.  Cases to be empty and washed by 9pm.

- RC to relocate and install Ice Cream Cases 39, 40, and 41.

- RC to relocate and install Case 2 (Held In Backroom).  RC to HOLD Case 38 in Backroom for install on Week 6.

- RC to accept delivery and install 12’ DX6LN (N84/A18).

Tuesday August 4- Day Work

- Reset Ice Cream cases 2, 39, 40, and 41, and NEW 12’ DX6LN Dairy.

Tuesday August 4- Night Work

- Store to Pull Product from Meat Promo Case 20.  Washed and Empty by 9pm.

- RC to remove Case 20 and GC to salvage

- GC and Plumber to begin trench work for NEW Promos that install next week.  New Promos to install on Monday Night of Next Week.  Work Wednesday and Thursday to have the trenches complete by End of This Week.

Week 6                                                                    Meat and Lunch Meat Departments

Sunday August 9- Night Work

- Store Personnel to Pull Product from Meat Cases 21, 22, 23, 24, and 25.

- RC to remove Meat Cases 21, 22, 23, 24, and 25.  GC to Salvage.

- GC to being working on repairing any damaged drywall, plumber to work on any drains that need to be moved.

- Trenches need to be inspected and complete by tomorrow night for case install

Monday August 10- Night Work

- RC to accept delivery and install 36’ LSB 95/200 Six-Deck Meat Cases (N80-83) and (2) 8’ QIL1 Promos.  RC to hold Case N83 in Back Room.  Cases to be operational by 8am.

Tuesday August 11- Day Work

- Fresh Specialist to be onsite today to reset Fresh Cases and Promos.

Tuesday August 11- Night Work

- Store Personnel to Pull Product from Cases 16, 17, 18, 19, 26, 27, 28, 29.

- RC to remove Cases 16, 26, 27, 28, and 29.  GC to salvage.

- RC to relocate and install Lunch Meat Cases 17, 18, and 19.  RC to relocate and install Case 38 (Being Held in Backroom) and install NEW 8’ LSB95/200 (Delivered Last Night). (TOTAL OF 5 Cases Installed Tonight)

- GC to repair any damaged drywall ahead of tomorrow nights case install.  Plumber to move any drains as needed.

Wednesday August 12- Day Work

- ***LUNCH MEAT RESET***

Wednesday August 12- Night Work

- RC to accept Delivery and install 28’ LSB 95/200 Six Deck Meat Cases (N75-N77) and 12’ DX6LD Produce Case.

Thursday August 13- Day Work

- Fresh Specialist to Reset 28’ Six Deck Cases and Produce Specialist to reset 12’ Produce Case.

Week 7                                                                                            Produce Department

Monday August 17- Night Work

- Store Personnel to Pull Produce Cases 10, 11, 12, 13, 14, and 15.  Washed and Empty by 9pm.

- RC to remove Cases 10 through 13.  GC to Salvage.

- RC to relocate and install 14 and 15.

- RC to accept delivery and install 24’ DX6LN (N72/72) and 4’ PF-Floral.

Tuesday August 18- Day Work

- Produce Specialist to be onsite to reset Produce Department.

Tuesday August 18- Night Work

- Store Personnel to Pull Product from Produce Tables

Wednesday August 19- Day Work

- Produce Specialist to be onsite to reset JSI Tables

- Final PRODUCE Reset

Week 8                                              Décor Start, Floor Start, Restrooms Start

Sunday August 23 through Thursday August 27- Night Work

- Floor Work (VCT) to begin this week. This work will be Sunday through Thursday and is scheduled to be a 4-week Process from Demo to Install.

- NOTE: Store is NOT TO UNLOAD any VCT Tile that shows up.  This unloading is handled by the Flooring Contractor.

- Restroom Remodels to begin tonight.  NOTE: GC has 3 weeks to complete both restrooms.  DO NOT START Restrooms UNTIL YOU HAVE ALL HARDWARE ON HAND.

- NOTE: Only one restroom will be available to customers during remodel.  The General Contractor is authorized to work both day and night in the restroom being remodeled to facilitate being complete

- General Contractor to install slide latch on Operational RESTROOM.  STRATEGY SPECIALIST to install Signage from Sign Kit on Restroom Doors

Monday August 24- Day Work

- NOTE: Electrician to have power in place for Bus-Strut fixture and is required to verify its operational with Décor Company.  This fixture is to have TWO (2) Circuits.

- Painter to begin Décor Removal and Wall Prep and Paint.  Décor Install on Week 10

- Coinstar to be removed this week.

Week 9                                               Front End Reset, Floor, Restrooms, and Décor Finish

Sunday August 20 through Thursday September 3- Night Work

- Flooring and Restroom Work continues this week.

- Wall Prep and Paint continues this week.

Monday August 31- Night Work

- Front End Reset:  Store to Close at 9pm tonight

- Front End Reset: T&A, 24” Workroom, 2 Comm Cabinets, 5 LH, 1 RH, 6’ CSC, 2 Grab-n-Go, Formula Cabinet.

- General Contractor to relocate front end minus ATM and Coinstar (install after Floor Tile Install)

- IT Vendor to terminate all front wall cat5 for lotto.

- IT Vendor to terminate DMO cat5.

- Mid-Carolina to make the check stand revisions.

- General Contractor to dispose of the removed check stands.

- Mandatory 9:00 pm meeting with IT Vendor and Mid-Carolina Electric to discuss tonight’s work.  Everyone’s cooperation is respectfully requested.

- Mid-Carolina is to provide pull strings for Muzak.

- Registers must be operational by 7 am the following morning.

- Electrical Contractor/General Contractor to have all front wall renovations finishes complete and electrical ready. To have all circuits relocated and cat5 ready for termination.

- Note: Clean power is to be ran to all PC’s (with orange receptacle)

- General Contractor is to have the office prepared this week for the installation of the new cash counting cabinet that will deliver tonight with the front end equipment.

Tuesday September 1- Day Work

- Merchandising to be on site to install PRODUCT at frontend.

- Muzak to be on site to install microphones on registers.

- Catalina Coupon is to install their equipment at the new kiosk and check stands.

- Southeastern is to install new lane lights

Week 10                                  Restrooms Finish, Flooring Continues, Outside Work Begins

Sunday September 6 through Thursday September 10- Night Work

- Flooring Continues

- Restrooms Finish

- NextGen Cabling by Vendor (Wachter) is to take place this week.  This work will take place at night Sunday through Thursday and will consist of pulling cables overhead throughout the store using a lift.  There should be NO Power Shutdowns this week.

- Loss Prevention to begin installation of upgrade of the security camera system this week.

- Outside work to begin ahead of Exterior Sign install on Week 12

Monday September 7- Day Work

- Project Manager and Job Superintendent “MUST” punch the store.

- SESCO to perform the punch list with their Energy Management Team and Test/Balance Sub.  The General Contractor must communicate to all subs are to be present at the time of SESCO’s inspection.

- Crescent Plumbing to perform a complete drain inspection on the store's sanitary sewer system.  General Contractor/Plumbing Contractor to work to complete any items discovered prior to Crescent's scheduled follow up visit.

- Décor Install to begin this week.

Week 11                                         Flooring Finishes, Gondola Movers Arrive, Outside Work

Sunday September 13 through Thursday September 17- Night Work

- Gondola Movers Arrive

- Flooring Contractor to finish this week

- GC to continue outside work

Monday September 14- Day Work

- Traffic Doors, Cart Corrals, and 24 Corner Guards to arrive.  GC to begin installing.

- Construction Supervisor to coordinate with the Retail Specialist, Project Manager and Superintendent to write the punch list.  Retail Specialist is to attend and generate their Soft Launch Assessment.

- General Contractor must complete this punch list by the End of Scheduled Construction Activity date.

- SESCO to forward their punch list to the Construction Supervisor and the General Contractor.  SESCO will perform a final inspection in 2 weeks. Make sure all items are complete prior to re-inspection to avoid additional trip charges.

- General Contractor must have ALL final inspections complete and obtain a CO.

- Décor install to finish this week.

Friday September 18- Day Work

- Electrical Work Deadline – Electrical Contractor to be complete with all electrical items found in bid notes and on plans by today in preparation of the Electrical Commissioning scheduled for Week 12.  Contact Anglea Hall at Crescent Construction (704 633 9697) for courtesy call from Crescent Technician prior to arrival.  Additional inspections and associated fees may result by not being ready on this date.

Week 12                                                                 Strip and Wax, Sign Package, Punch Week

Monday September21- Day Work

- Exterior Sign Package to Deliver and Install

Monday September 21- Night Work

- Strip and Wax to begin.  This is a two-night process and if the date needs to be changed, please communicate that request to me.

- GC to work on Punch List Items remaining days of week.

Week 13                                                             Case Painting, Vestibule Carpet, Punch Week

Monday September 28- Day Work

- Crescent Construction to perform electrical commissioning report this week.

- Energy Team will conduct a complete store RCC, General Contractor to complete any items as soon as the report is available.

Monday September 28- Night Work

- Case Painting to begin.  This could be up to 3 nights.

- GC to continue Punch List Items

Thursday October 1- Day Work

- Vestibule Carpet to install

- Coinstar and ATM to reinstall

Friday October 2- ***End of Scheduled Construction Activity (technical punch continuation) ***

- General Contractor must submit all final change orders by this date.

Week 17                                                                                              Technical Punch Deadline

Friday October 30 - ***Technical Punch Deadline***

- General Contractor and all Sub Contractors to be complete without exception.  Any remaining items will be turned over to the Food Lion Construction Manager, Mike Eason, to work directly with the General Contractor.

Sincerely,

BUILDING OUR FUTURE...

MATT PHILLIPS

Construction Manager

MP/sfc

2560schdraft